## Sheet1
Table 1: Canadian Mountain Network Annual Research Progress Table
| Current Fiscal Year | [5 empty] | Future Fiscal Years
Date | Year of Project | Goals | Objective | Performance Indicator/ Measure | Outcomes | When Life Happens!
Please record the date that this information is being entered | Please list for the current fiscal year and then continue to add to this table for cumulative reporting as your research progresses through the years | Goals are general statements explaining what you wish to achieve. Please state your research goals as stated in your original application or as intended in your original application. If your goals have changed, please indicate your new goal and provide an explanation as to why your goals have changed and developed. If you have new future goals for subsequent years, please identify those as well for CMN's planning purposes. You may have multiple goals for a single year. If so, please list each goal on a separate row. | Objectives define strategies or implementation steps to attain the identified goals; How you intend to achieve your goal. You may have multiple objectives for a single goal. If so, please list each objective on a separate row. Unlike goals, objectives are specific, measurable and have a defined completion date. Please state your research objectives as stated in your original application or as intended in your original application. You may have stated these as deliverables originally. If your objectives have changed, please indicate your new objective and provide an explanation as to why it has changed or developed. | Indicators measure a project or programs activities and outputs, progress towards your objectives and evidence of progress towards your goals. Please describe your progress or performance toward each objective. | Outcomes are the benefits of change or impacts to the end users of the research or those involved in your research to date. Outcomes can be short-term, medium-term or long-term. Short-term outcomes produce changes in learning, knowledge, attitude, skills or understanding. Medium-term outcomes produce changes in behaviour, practice or decisions. Long-term outcomes produce changes in condition. Each goal can have multiple objectives and each objective can have multiple outcomes. Please include outcomes realized for research, training (e.g., HQP) and knowledge mobilization in this fiscal year. Please refer to Table 2 where needed. | Please explain areas where you overachieved and why that happened or areas where you were unable to meet your outcomes, the challenges you faced and how you will address those challenges. Please also identify any areas where CMN could support you to better navigate when life happens! This includes specific pivots or changes needed to address COVID. | Please complete all columns B, C, D & E for all years of your project. Use this column to comment or identify any changes that you are anticipating to your goals, objectives, indicators, for future years.
2021-12-10 | 2021-2022 | Build partnerships | Quarterly meetings of anIndigenous-led NNP Hub Steering Committee and monthly partner meetings (including participation by other complementary CMN hubs), Develop program evaluation framework, Participation (#, frequency) of other CMN hubs, especially Porcupine Caribou. | Participation (#, frequency) of other CMN hubs, especially related to Porcupine Caribou Herd and Mi'gmaq Maliseet Aboriginal Fisheries Management Association; Steering Committee and partner meetings (#); Participation level (#, diversity of organizations represented, minutes); Annual program evaluation. | Community plans for the mountains are recognized and supported by partners across jurisdictions, as well as wildlife managementauthorities within and across the regions encompassed by the NNP Hub. Relationships are established with others with shared interests in reconciliation and biocultural approaches to caribou conservation, including other Indigenous communities, non-Indigenous harvesters, as well as social and natural scientists and other allies. | We were successful in organizing a preliminary NNP Hub meeting this year where we discussed research license and ethics applications and explored research relationships and future collaborations and also dicussed about the process of establishing a Steering Committee. | NA
2021-12-10 | 2021-2022 | Cross-cultural knowledge sharing-Indigenous and local knowledge and science | Build skills, knowledge and confidence in community conservation planning by coordinating Healthy Country Planning Training and other training/mentorship opportunities related to planning and Indigenous Knowledge documentation. | # of: Mentorships established; Training sessions; Participants/organizations represented; Debriefs with feedback, participant confidence (closing circles, group discussions and surveys). | IK transmission to present and future generations; IK as baseline for monitoring change (people and environment), including as part of Nę K'ǝ́dı́ke programming; IK made available for use in community conservation planning and decision-making; IK serving as justification for achieving IPCA status. | We are still at the initial phase of establishing the Hub and preoccupied with program initiation, hence much to report on this topic | The expectation is that there will be more opportunities for on the land experience including research and training opportunities in 2022 which would support and strengthen the cross-cultural knowledge sharing initiative.
2021-12-10 | 2021-2022 | Establish Nı́o Nę P'ęnę́ (NNP) GIS Hub | Establish an ArcGIS Hub, which will provide the knowledge holders and community members to share their knowledge and all geographic content in a secure, cloud-based environment hosted by Environmental Systems Research Institute (ESRI). Data provided by the knowledge holders andcommunity members will be in the form of maps (spatial data), audio, images, documents,and/or tabular data. | Steering committee and partner meetings; participants/organizations represented; debrief sessions with feedback; one-on-one conversations with partners to facilitate the data sharing in form of maps, audio, images, documents, or tabular data; training session for community members to help them understand the working of Hub for their use. | Online documentation of IK in a secure cloud-based environment, also known as Arc GIS Hub, by and for the community members and Knowledge holders. The ArcGIS Knowledge Hub will support meaningful application of OCAP (Ownership, Control, Access, and Possession) principles in research with Indigenous peoples, insofar as the platform will provide a user-friendly interface with both science and Dene/Métis information. | The SRRB has put a lot of effort into establishing the platform for the Hub. Nature United (NU) is actively supporting HQP, with a focus on Guardian training/program research. NU is also a key support for theGIS Hub and has been working on building training sessions for HQP and reserach manager, Manisha Singh. Additionally, ESRI license has already been purchased and an ArcGIS Online (AGOL) Organizational Account which will provide the platform to set up the GIS Hub for community members. | In partnership with Nature United, the project team decided to embark on the GIS Hub project as a vehicle for adhering to OCAP principles.
2021-12-10 | 2021-2022 | Prepare/present evidence to2021 Public Listening Session (PLS) | Supporting a planning workshop in each community addressing the the central question, "What should people's role be in maintaining healthy relationships between caribou and people?" | Workshop in each host community with identified resource people (#, report); depth of engagement,satisfaction of work produced in workshop (closing circle, debrief interviews / survey / knowledge self-assessment); support community-driven planning, knowledge-sharing and research, and youth/Guardian and women's; planning, research and knowledge activities; support implementing decisions/ recommendations emerging from plans and PLS reports to dat; # of: community driven initiatives; participants, including diversity of voices represented; Indigenous and science research projects initiated, continued or expanded (ex. braided caribou knowledge and genetics). | The series of five SRRB PLS are hearings under the Sahtú Dene and Métis Comprehensive Land Claim Agreement, formally recognized in Canadian administrative law. Through the PLS, Tuliı́t'a and Norman Wells panels (including representatives of local and District leadership organisations) have opportunities to present evidence arising from NNP research and how research results inform community conservation plans; participants in the PLS include all five Sahtú communities, governments, environmental non-governmental organisations, and the public. The SRRB in turn weighs the evidence presented and makes decisions and recommendations that must be considered by the Government of the NWT Minister as a basis for final decisions. Thus the PLS represent a hugely impactful venue for both knowledge dissemination and mobilization. | Norman Wells and Tulı́t'a have had strong participation to date in PLS activities in preparation for the 2021 PLS. However, COVID contingencies led to several delays, and the rigours of remote work were very challenging, especially during the Sahtú COVID outbreak. Another challenge has been uneven capacity in planning, which combined with COVID distancing measures has proven to be an insuperable barrier for Tulı́t'a in recent months. | The Tulı́t’a and Norman Wells communities are registered to present at the virtual PLS scheduled for February 2022 (deferred from 2021); Tulı́t’a will host a second PLS in 2022 on the topic Wildfires and Climate Change, with submissions including results from the NNP research.
2021-12-10 | 2021-2022 | Foster implementingprevious PLS decisions/recommendations | Foster effective participation inthe 2021 PLS onCaribou Predators and Competitors, incorporating carry-over topics from the 2020 session (on harvest regulation). | # of: Organizations represented through PLS presentations; Diversity of voices presenting (ex. women, Elders, youth, harvesters, leaders, scientists and other collaborators); PLS report decisions/ recommendations; Presentations and publications. | See above | See above | See above